## 模块总览
模块 | 规划页面 | 开发状态 | 列表页 | 详情页 | 新建/编辑 | Service | 备注
用户权限 | 用户管理/角色管理/权限管理/个人设置 | 已完成 | Y | - | Y | - | 含状态切换、角色分配、密码重置
组织管理 | 供应商/商家/司机/车辆 | 已完成 | Y | - | Y | - | 4个子模块均完整
商品管理 | 商品/分类/标签/关键词/SKU/条码/供应商/可见性/补货提醒 | 已完成 | Y | - | Y | - | 9个子页面，含SKU多维度管理
采购管理 | 采购单/采购退货/待采清单 | 已完成 | Y | Y | Y | Y | PurchaseService + PurchaseReturnService
订单管理 | 订单/购物车/退货/常购/复购模板 | 已完成 | Y | Y | Y | - | 含状态流转、改价、锁定
库存管理 | 仓库/库存/库存日志/拣货任务 | 已完成 | Y | Y | Y | Y | InventoryService + 单位换算
物流配送 | 线路/任务/送货单/签收/差异/温度/车辆故障 | 已完成 | Y | Y | Y | - | 7个子模块，线路含商家排序
损耗管理 | 损耗单 | 已完成 | Y | - | Y | Y | LossOrderService
价格管理 | 促销(8种)/取价配置/改价记录 | 已完成 | Y | - | Y | Y | PricingService，5来源取价
系统管理 | 配置/审计/登录日志/轮播/审核/审批/单位 | 已完成 | Y | - | Y | Y | ApprovalService + UnitConversionService
财务管理 | 充值/结算/应收/发票/更正授权/均摊/商家账户 | 部分完成 | Y | - | 部分 | - | 列表页已有，详情/流转待完善
商家功能 | 商家地址/商家收藏 | 部分完成 | Y | - | 部分 | - | 基础CRUD有，小程序端未开发
通知系统 | 通知抽屉 | 部分完成 | Y | - | - | - | 仅UI展示，推送逻辑未接入
商家端小程序 | Taro 4 + React | 未开发 | - | - | - | - | 下单/购物车/常购/复购/收藏
司机端小程序 | 原生微信小程序 | 未开发 | - | - | - | - | 接单/导航/签收/温度/轨迹
实时推送 | Laravel Reverb WebSocket | 未开发 | - | - | - | - | 订单状态/配送追踪实时推送
券核销 | 优惠券领取/核销 | 未开发 | - | - | - | - | 表已有，业务逻辑未开发
微信生态 | 微信用户/授权/模板消息 | 未开发 | - | - | - | - | 表已有，OAuth/消息未开发
AIGC:2a2473d2-822f-4aa3-96d6-ef71a4e01ba6 | {"Label":"1","ContentProducer":"001191110102MAD55U9H0F10002","ProduceID":"2a2473d2-822f-4aa3-96d6-ef71a4e01ba6","ReservedCode1":"4eb2f2d6-3c85-4120-aa5b-ea1210839d48","ContentPropagator":"001191110102MAD55U9H0F10002","PropagateID":"2a2473d2-822f-4aa3-96d6-ef71a4e01ba6","ReservedCode2":"4eb2f2d6-3c85-4120-aa5b-ea1210839d48"}

## 数据库表统计
模块 | 表数量 | 主要表
用户权限 | 6 | users, roles, permissions, model_has_roles, model_has_permissions, role_has_permissions
组织管理 | 5 | suppliers, merchants, drivers, vehicles, driver_vehicles
商品管理 | 12 | products, product_images, product_tags, categories, tags, keywords, skus, sku_barcodes, sku_suppliers, merchant_sku_visibility, restock_reminders, store_sku_prices
采购管理 | 5 | purchase_orders, purchase_order_items, purchase_returns, purchase_return_items, purchase_items
订单管理 | 9 | orders, order_items, order_returns, order_return_items, carts, cart_items, frequently_bought, repurchase_templates, repurchase_template_items
库存管理 | 5 | warehouses, inventory, inventory_logs, picking_tasks, picking_task_items
物流配送 | 13 | delivery_routes, delivery_route_stops, delivery_tasks, delivery_task_details, delivery_task_sequences, delivery_notes, delivery_note_items, delivery_tracks, delivery_arrival_logs, signatures, temperatures, discrepancies, vehicle_issues
损耗管理 | 2 | loss_orders, loss_order_items
财务管理 | 10 | merchant_accounts, recharges, supplier_settlements, supplier_settlement_items, settlement_payments, receivables, receivable_payments, invoices, correction_authorizations, price_apportionments
价格管理 | 14 | promotions, promotion_skus, promotion_flash_sales, promotion_group_buys, promotion_full_reductions, promotion_bundles, promotion_bundle_items, promotion_coupons, promotion_clearances, promotion_member_discounts, featured_promotions, price_strategies, price_strategy_items, price_change_logs
系统管理 | 11 | system_configs, banners, audit_logs, operation_logs, approvals, approval_type_configs, units, unit_conversions, notifications, wechat_users, login_logs
合计 | 96

## 代码统计
维度 | 数量
Livewire 组件 | 70
Blade 视图 | 70
Eloquent Model | 70
数据库表 | 96
Service 类 | 7
路由 | 81
通用 Trait | 7
系统角色 | 10
权限点 | 203